## Features
Spend Features
Last Revision | 04-14-2020
Release Version | Feature | Description | Status | Notes | Commit
2.1 | BMO Compatibility | Make BMO Statements Compatible with System by adding to BankFormat Enum structure | Not Started

## Bugs V2.0
Spend Bug Report
Version | 2
Last Revision | 04-14-2020
Bug No. | Date | Problem | Description | Importance | Current Status | Notes | Commit ID
1 | 04-14-2020 | Statement Loading Error | Some statements in the selected directory do not load into the system Changing the names of the files has proven to be successful in some cases and not others | HIGH | Fixed | Issue occurred when the transaction id string contained a comma value which mess up the transaction line indexiing. Fixed by centralizing the transaction format (created BankFormat enum) and checking to make sure each line item was the appropriate length before proceeding to parse values. If the actual length does not match the desired length, the line is shorteded by merging the id string and the adjacent string. Future Risk: The system may encounter an issue if any further formatting issues occur (ie. numbers in the wrong place) | f2aeae5ef920ec3fdea608e5de2329cda4c40e27
2 | 04-14-2020 | Maps not saving | ID-Mapped transactions are not saving to the id_map.json file when using the save button or closing the program The ID-map is populated with all transactions that are mapped via substring | HIGH | Unresolved
3 | 04-14-2020 | Statement Loading Pt. 2 | Changing the name of the file seemed to allow statements to be imported. Error could also be due to table not refreshing (cannot confirm that values were not imported and simply not being displayed) | MED | Unresolved